## Gantt Chart Template
THE FUTURE OF COMPUTING IN AI,AR AND VR
Name: LORO JOHN VIANNEY
| MILESTONES | Start (Date) | End (Date) | Duration (Days)
| IDEATION | 2023-01-01 | 2023-01-30 | 29
| Gather Data | 2023-01-01 | 2023-01-14 | 13
| Create Charts | 2023-01-15 | 2023-01-17 | 2
| Create Budget | 2023-01-18 | 2023-01-20 | 2
| Write Proposal | 2023-01-21 | 2023-01-31 | 10
| PROJECT INITIATION | 2023-02-01 | 2023-02-14 | 13
| Creating my team | 2023-02-07 | 2023-02-14 | 7
| PROJECT PLANNING | 2023-02-15 | 2023-02-28 | 13
| Define Requirements | 2023-02-20 | 2023-02-28 | 8
| PROJECT EXECUTION | 2023-03-01 | 2023-03-31 | 30
| Design and Prototyping | 2023-03-01 | 2023-03-14 | 13
| Software Development | 2023-03-15 | 2023-03-30 | 15
| Testing | 2023-04-01 | 2023-04-15 | 14
| Implement | 2023-04-16 | 2023-04-29 | 13
| PROJECT CLOSURE | 2023-04-30 | 2023-04-30 | 0

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!